## Slide 1: Danube Region Strategy
Knowledge Society
VITAJTE 
PA7 SK tím míting 16 November 2020

## Slide 2: WPT1 Policy development
Analysis of PA7 actions relared to Horizon 2020 and for Horizon Europe – by 12/2020 – 2 questionnairs surveying the participation and policy makers opinion are in progress
Workshop to Horizon Europe 6/2021 – will follow after analysis of inputs from survey
Final output will be summerized in
Policy report and recommendation connected to Horizon Europe
Capitalization – Cooperation to MRSs – via Interact initiative we collect good practices on remote learning and education across MRSs
Cooperation and establish new links to qualdruple helix – in progress
Pilot Working groups – DFCN shared good practice and template, building up 2 working group is in progress
SG meetings – 1st in June 2020, online only
First progress report to JS submited on Sep 30, 2020, so far no feedback, in eMS it shows submited to CA
Communication activities on FB, Twitter and web page
WPT2 Cooperation and coordination
WPM: Coordination, communication and management

## Slide 3: Problems and risks
Due to covid 19 outbreak, the planned meetings had to be moved to the online platforms instead to substitute the personal meetings, the situation furthermore delayed several activities and caused leftovers and underspending compared to the planned budget in the approved AF:SCSTI (LP) was not able to organize a in-person SG meeting which caused a leftover in amount of 4900 € (BL EE).
Both partners were not able to participate in activities that are in AF foreseen as face-to-face meetings in all WPs, the leftover in BL Travel for period 1 is: 5563 € for LP and 4180 for UoB
Underspending occurred also in staff costs caused by prolonged project contracting process further affecting the staff contacting and time to find adjustments of activities that were foreseen to be done in the workplace, this is more prominent in LP budget where the leftover is 11 430 € and UoB is 1811 €.
The spending on project level reached 37 % of allocated funds for the period 1 (LP´s spending was 31 % and UoB 53 % of allocated funds for the period 1), partners are committed to catch up with spending and find adjustments of actives that need to be modified due to existing situation. Also, the reach of the target groups and networking with relevant stakeholders is significantly lower due to the restrict