## Slide 1
Working Group
Danube Funding Coordination Network
PA7 Steering Group Meeting
02 June 2021

## Slide 2: DFCN suggested steps for implementation
Action | Working Group and ideas and concrete steps to take | Status / envisaged activities
1: To promote coordination of national, regional and EU funds to stimulate excellence in R&I, in research areas specific for Danube Region | Screening of the HE Work Programmes for application possibilities Consider a EUSDR/PA7 specific input to the ERA document once available Screen the new ERA communication for potential activities within the EUSDR If seed-money kind of funds are available – call for ideas for future flagship projects in the region | Huge delay in the publication of the HE Calls, now foreseen for 22nd of June Limited stakeholder consultations so far ERA Forum for Transition has started its work – inclusiveness is one of the ERA principles Seed money availability not clear yet
2: To promote participation of Danube countries in EU R&I Programmes, in particular in Horizon Europe | Continuation of multilateral Call activities Screening of the HE Work Programmes for application possibilities Continue RI mapping and exploit sharing concepts in the EUSDR (maybe in cooperation with ESFRI and or the JRC) Include plans for Teaming in the national plans for the structural funds | Next Call envisaged for 2022 – invitation for countries to join Analysis of the participation of EUSDR in the European partnerships and possibilities for AC to join New S3 documents and Strcutural funds plans are currently being finalised by MS that may include references to Teaming
3: To strengthen cooperation among universities, research organisations and SMEs in the Danube Region | Consider a cross-border EUSDR COST info day / webinar Consider a matchmaking event for EUSDR for the first Twinning Call Explore good examples of academia/business cooperation for further implementation across the EUSDR (cooperation potential with PA8) | 

## Slide 3: DFCN suggested steps for implementation
Action | Working Group and ideas and concrete steps to take | Status / envisaged activities
4: To increase awareness and visibility of science and innovation in the Danube Region | Explore the possibility to use the structural funds more extensively for Seal of Excellence projects e.g. in Marie Curie | Collect good practis examples from Member States also based on the Work Shop of 18th of June 2021
5: To support exchange of information and experience sharing for the purpose of preparation of future strategic R&I documents applicable in the new programming period | To continue close cooperation with national and EU institutions in charge (in particular with the JRC). | 
6: To promote horizontal cooperation in science and technology across all PAs and other MRS |  | 

## Slide 4: DFCN suggested steps for implementation
Action | National, bilateral and multilateral EUSDR activities ongoing or planned to support the actions
1: To promote coordination of national, regional and EU funds to stimulate excellence in R&I, in research areas specific for Danube Region | Multilateral Danube Call (coordination BMBWF Austria) Support of flagship project DREAM (BMBWF)
2: To promote participation of Danube countries in EU R&I Programmes, in particular in Horizon Europe | Bilateral Call AT-SK in preparation to support collaboration in selected Widening Calls
3: To strengthen cooperation among universities, research organisations and SMEs in the Danube Region | Multilateral Danube Call Danube Rectors Conference
4: To increase awareness and visibility of science and innovation in the Danube Region | Danubius Award and Danubius Young Scientist Award sponsored by the BMBWF Austria – Call deadline extended until 15th of June 2021 for DYSA
5: To support exchange of information and experience sharing for the purpose of preparation of future strategic R&I documents applicable in the new programming period | Share current documents on S3 and / or Strcutural Funds once they are available
6: To promote horizontal cooperation in science and technology across all PAs and other MRS | Not directly applicable